## Slide 1
December 15, 2020
Co-Chairs:
Bill Lober
University of Washington
John Loonsk
Johns Hopkins University
Making EHR Data More Available for Research and Public Health (MedMorph)
Technical Expert Panel (TEP)

## Slide 2
TOPIC |  | LEAD(S) | TIME (ET)
1 | Logistics & Welcome | Wendy Blumenthal TEP Co-Chairs: Bill Lober, John Loonsk | 3:00 - 3:05
2 | HL7 Ballot Process | Jamie Parker | 3:05- 3:20
3 | HL7 Ballot Update | Nagesh Bashyam | 3:20- 3:40
5 | USCDI Update | Becky Angeles | 3:40 - 3:45
6 | Year-in- Review | Jamie Parker | 3:45 - 3:55
7 | Announcements, Next Meeting January 19, 2021 | Bill Lober John Loonsk MedMorph Project Team | 3:55 - 4:00
MedMorph TEP Meeting Agenda – 12/15/2020

## Slide 3: HL7 Ballot Process
Jamie Parker

## Slide 4: HL7: Deliverables and Artifacts
Date | Artifact | Status
February 20, 2020 | Draft PSS Presented to the HL7 Supporting WG | Complete
February 21, 2020 | Submit PSS Scope Statement for September 2020 Ballot Cycle | Complete: https://confluence.hl7.org/display/PHWG/Making+EHR+Data+More+Available+for+Research+and+Public+Health+%28MedMorph%29+Reference+Architecture+HL7+FHIR+Implementation+Guide
April 19, 2020 | HL7 Steering Division Approval | Complete, PSS Approved
July 21, 2020 | Connectathon Proposal | Complete
September 9-11, 2020 | HL7 FHIR Connectathon – Virtual (https://www.hl7.org/events/fhir/connectathon/2020/09/ | Complete (successful exchange achieved)
September 21-25, 2020 | HL7 Workgroup Meeting – Virtual | Complete
October 18, 2020 | Submit FHIR IG Proposal | Complete: https://confluence.hl7.org/display/FHIR/Making+EHR+Data+More+Available+for+Research+and+Public+Health+%28MedMorph%29+Reference+Architecture
November 1, 2020 | Submit Notice For Intent to Ballot (NIB) | Complete: http://www.hl7.org/Special/committees/tsc/ballotmanagement/reviewNIBs.cfm
November 1, 2020 | Substantive IG complete | Complete
November 24, 2020 | Ballot Freeze | Complete
December 13, 2020 | Ballot Due | Complete
December 18, 2020 | Ballot opens for voting | 
January 13-15, 2021 | January HL7 Connectathon | 
January 25-29, 2021 | January HL7 WG Meeting | 
https://confluence.hl7.org/display/HL7/HL7+Calendars#a024f57c-d5fc-4f39-8b26-bf9f1e280100-35717172

## Slide 5: HL7 Ballot Checklist (1/2)
 | Activity | Completed
 | Present a Project Scope Statement for approval from sponsoring workgroup and HL7 Leadership | February –April 2020
 | Attend HL7 WG meeting and participated in the WG meeting Connectathon | Sept 2020
 | Presented Notice for Intent to Ballot (NIB)to HL7 sponsoring WG (Public Health) for approval | Oct 2020
 | Submitted NIB | Nov 2020
 | Conducted MedMorph specific connectathon to satisfy ballot requirements (3 different entities must test IG prior to ballot) | Nov 2020
 | Review “Substantively Complete” IG with HL7 sponsoring WG (Public Health) for approval | Nov 2020
 | Submitted “Substantively Complete” IG | Nov 2020
 | Updating IG based on feedback from MedMorph Community and Connectathon | Nov 9-24, 2020
 | Ballot Content Freeze | Nov 24, 2020
 | Ballot is approved and reviewed by sponsoring WG (Public Health) and FHIR management | Nov 24- Dec 3, 2020
 | Final approved IG Ballot submitted | Dec 13, 2020

## Slide 6: HL7 Ballot Checklist (2/2)
 | Activity | Completed
 | Sign up for the MedMorph IG Ballot | Nov 16 - Dec 17, 2020
 | Vote and submit comments to the MedMorph IG Ballot | Dec 18, 2020 - Jan 18, 2021
 | HL7 WG Meeting Connectathon | Jan 13 - 15, 2021
 | Ballot voting closes | Jan 18, 2021
 | Prepare comments for disposition | Jan 18 - 25, 2021
 | Attend January 2021 HL7 WG Meeting (Virtual) | Jan 25 - 29, 2021
 | Disposition ballot comments | Jan 18 - Apr 1, 2021 (depending on how many comments)

## Slide 7: Next Steps for the RA IG and the Ballot Process
Sign up for the Ballot Pool by Dec 17th
  In order to formally vote and comment on any ballot proposed by HL7, an individual MUST sign up to be part of the ballot pool prior to the ballot opening
  HL7 Members: http://www.hl7.org/ctl.cfm?action=ballots.loginchoice (you will need to login with your HL7 credentials)
  Non-Members (fee assessed): http://www.hl7.org/ctl.cfm?action=ballots.login
https://confluence.hl7.org/display/HL7/HL7+Balloting

## Slide 8: Joining the Ballot Pool – HL7 Members
You will need to go to the HL7 website: http://www.hl7.org/ and log in.
Once you are logged in you will go to the ballot desktop page: http://www.hl7.org/ctl.cfm?action=ballots.loginchoice (note you may need to login again)
  If you need to login again select “Already a Member”
Once you have accessed the Ballot desktop on the Right Side of the page select "Join Consensus Group“
Once you join the Consensus Group you will see a list of ballots. Scroll down until you see "HL7 FHIR® Implementation Guide: Making EHR Data More Available for Research and Public Health (MedMorph) Reference Architecture, Release 1- US Realm“
Select the checkbox next to the ballot
Scroll to the bottom of the list and select "Join These Marked Ballots Consensus Groups"
You are not signed up for the MedMorph Ballot

## Slide 9: Ballot Voting Options
Vote | Description
Abstain | The balloter has reviewed at least some of the ballot material but has not formed an opinion on whether the specification should be approved or not. Abstentions count towards quorum, but not towards whether the ballot passes or not.
Affirmative | The balloter may have some feedback about minor changes they would like to see (typos, small suggestions, etc.) but are overall comfortable with the specification and are happy to see the specification published even if none of their comments result in changes to the specification. This vote cannot occur if the balloter has submitted any "negative" comments.
Negative | At least one of the balloter's comments was marked as "negative", meaning the balloter feels the specification must not be published until all issues they marked as negative have been appropriately addressed.
No vote | No vote has been recorded. This is the initial state for the ballot submission. If no action is taken by the voter, this will be the voter's final submission status. A "no vote" means that the ballot submission won't count towards quorum.
Removed | After initially signing up as a voter, the user has been removed from the voting pool. This may be based on user request or due to a lapse of membership.
https://confluence.hl7.org/display/HL7/HL7+Balloting
Vote and Comment:
  Ballot opens for voting December 18, 2020- January 18, 2021
  Once the ballot is open and you have signed up for the ballot pool you may cast your ballot

## Slide 10: Voting on the MedMorph IG – Non HL7 Member
If you are not an HL7 member and have comments, you can send them to the MedMorph project team to submit them “on behalf” of the MedMorph Community
  Jamie.parker@carradora.com
  becky.angeles@carradora.com
We will send out an email early next week to the TEP and Reference Architecture Listserv reminding the community the ballot is open
  Email will contain directions on how to submit comments – HL7 Members will follow HL7 balloting process
  For non-HL7 members
    Your name, email address and organization
    Hyperlink to the IG page which you are making comments
    Section name
    Subsection name
    Sentence/word/paragraph that you are making comments (can copy the text and use track changes to indicate your comment)
    Make comment if it is general based on what section of the IG you are commenting

## Slide 11: HL7 Next Steps
Register for January Connectathon (Jan. 13-15, 2021)
  Registration is open: http://www.hl7.org/events/fhir/connectathon/2021/01/
    $150.00 for Members (early bird Dec 30) – $250 (
    $250.00 non-members (early bird Dec 30) – $375
  Coordinate with Public Health Tracks
    Harmonization with eCR
  Allow time for implementers to build software based on IG
  Focus on the individual use cases and test data for each use case that can be exercised
  Focus on harmonization with eCR and other public health tracks to ensure compatibility
Register for Jan 2021 HL7 WG Meeting (Jan 25-29)
  http://www.hl7.org/events/working_group_meeting/2021/01/
    Member fee $200.00 (early bird registration ends Jan. 11, 2021) - $300
    Non-Member fee $350.00 (early bird registration ends Jan. 11, 2021) - $525
    During the HL7 Workgroup Meeting MedMorph will be presenting to the Public Health Working group on
      Wednesday, January 27th https://confluence.hl7.org/display/PHWG/2021-01+WGM+Agenda

## Slide 12: HL7 MedMorph Reference Architecture Ballot Update
Nagesh Bashyam

## Slide 13: Timeline: MedMorph Activities & IG Balloting
March
April
May
June
July
August
September
October
November
December
January 2021
MedMorph Use Case Development
End to End Use Case Review
Finalize Use Cases
Prepare HL7 Reference Architecture (RA) FHIR IG
HL7 Notice for Intent to Ballot Due
HL7 RA FHIR IG submitted
HL7 Working Group Meeting
HL7 PSS Submitted
MedMorph Project Activities
HL7 Processes
Legend
HL7 Sept 2020 FHIWG Meeting

## Slide 14: Making EHR Data More available for Research and Public Health (MedMorph) Reference Architecture IG
All approvals needed by HL7 and the Public Health Workgroup were received
The ballot was submitted per the deadline of Dec. 13, 2020
The RA on the MedMorph RA Confluence has been incorporated into the FHIR IG Build and can be found here:
  http://build.fhir.org/ig/HL7/fhir-medmorph/
Notes: URL for Ballot: hl7.org/fhir/us/medmorph/jan2021/index.html

## Slide 15: USCDI Updates
Becky Angeles

## Slide 16: MedMorph’s Submission to USCDI ONDEC
MedMorph analyzed data elements from the multiple MedMorph use cases. Identified elements that were used by 2 or more use cases that were not existing in USCDI
Submitted 76 data elements to be considered added to USCDI
  43 MedMorph elements were assigned Level 2
  6 MedMorph elements were assigned Level 1
  17 MedMorph elements were assigned Comment Level (Note that we may provide additional comments to try to push these up to Level 1 or Level 2.)
  6 MedMorph elements were considered to be duplicates of existing USCDI v1 elements
  4 MedMorph elements are unknown
A BIG thanks to all who contributed time, effort, brain power – especially:
  Wendy Blumenthal, Cindy Bush, Steve Eichner, Brian Gugerty, Genny Luensman, Craig Newman, Jenna Norton, Sameemuddin Syed

## Slide 17: USCDI ONDEC Timeline
Step 1. Submit new data elements and classes (CLOSED October 23, 2020)
Step 2. ONC evaluates and assigns a level to each data element depending on the overall value, maturity and challenges to implementation (In Progress/Complete?)
  • Comment • Level 1 • Level 2
Step 3. ONC posts submitted data elements on the USCDI page by level (In Progress/Complete?)
  Submitters will have an opportunity to add or change information which could change its level determination.
  Other stakeholders can review these submissions and contribute to their development through comments and collaboration with original submitters.
Step 4. Submissions achieving Level 2 by October of each year will be considered for inclusion in the draft of the next version of USCDI. ONC will present the draft to the Health IT Advisory Committee and the public for comment. (In Progress?)
Step 5. ONC finalizes the next version of USCDI (July 2021) .

## Slide 18: Year in Review and Next Steps
Jamie Parker

## Slide 19: 2020 Accomplishments (1/2)
137 Community Members that participated in TEPs, Use Case Workgroups, Consolidated Use Case Workgroup, Reference Architecture workgroup, Evaluation Workgroup
Use Cases
  Kicked off and established Use Case Workgroup (first part of year we had 3 use case WG calls that combined to 1 call in May)
  Completed first drafts of 3 main use cases (Cancer Reporting, Healthcare Surveys, Hepatitis C Reporting)
    Description, Problem Statement, Goals, User Stories, Scope, Actors, Abstract Model, Use Case Flow and Diagrams, Dataset Requirements, Policy Considerations, Non-Technical Considerations
  Identified common data elements for submission to United States Core Data for Interoperability (USCDI)
  Completed cross-walk to identify commonalities across use cases
Reference Architecture
    Submitted a Project Scope Statement to HL7 that was accepted by (presented to Public Health, FHIR Management, US Realm Steering Committee)
    Completed 5 main workflows describing actors and their interactions
    Prepared Notice for Intent To ballot
    Drafted a MedMorph Implementation Guide as part of ballot readiness: http://build.fhir.org/ig/HL7/fhir-medmorph/index.html
    Tested several workflows during November 9, 2020 Connectathon
    Preparing for January HL7 ballot

## Slide 20: 2020 Accomplishments (1/2)
Evaluation Plan development in progress
  Completed Short- and Long-Term Evaluation Model
  Completed Short Term Evaluation Plan
  Developing requirements for Long Term Evaluation Plan
TEP
  Held 8 TEP meetings
  StayHome.App, eCR Now, Common Data Model Harmonization Phase 2 (CDMH), CodeX, MCC eCare, Exploring Interoperability Between Electronic Health Records (EHRs) and Electronic Death Reporting System (EDRS) using FHIR, The Next Phase of Electronic Birth Defect Reporting (BDR), Louisiana Public Health Institute (LPHI) REACHnet Research Use Cases
USCDI
  Submitted 76 data elements to be considered added to USCDI
    Including all necessary data as part of the submission
    Reconciling any comments received from ONC regarding the submission

## Slide 21: MedMorph: Deliverables and Artifacts
Artifact | Location
Reference Architecture Confluence Page | https://carradora.atlassian.net/wiki/spaces/MedMorph/pages/545914881/Reference+Architecture+Document
Health Care Survey Use Case Confluence Page | https://carradora.atlassian.net/wiki/spaces/MedMorph/pages/692060180/Health+Care+Survey+Use+Case+-+DRAFT
Hepatitis C Use Case Confluence Page | https://carradora.atlassian.net/wiki/spaces/MedMorph/pages/694452251/Hepatitis+C+Use+Case+-+DRAFT
Cancer Use Case Confluence Page | https://carradora.atlassian.net/wiki/spaces/MedMorph/pages/699990019/Cancer+Use+Case+-+DRAFT
Research Use Case Confluence Page | https://carradora.atlassian.net/wiki/spaces/MedMorph/pages/858980359/Research+Use+Case+-+DRAFT

## Slide 22: Next Steps – Plans for 2021
Reference Architecture Workgroup
  Will work to get the RA IG ready
  Monitor incoming ballot comments
  Work with the RA WG to review comments and draft formal dispositions
Use Cases Workgroup
  We will convene as needed until February
    Update use cases with additional data elements or ballot comments
    Monitor IG ballot comments that are Use Case specific
      Draft dispositions will be done on the RA WG call - please join the RA WG meetings on Wednesdays to help in drafting dispositions
  Starting in February 2021 - Develop the Use Case Content Implementation Guides
Evaluation Workgroup
  Continue working on Short Term Evaluation Plan
    If interested in joining the RA WG calls for draft ballot dispositions, please let Jamie know

## Slide 23: Closing
Wendy

## Slide 24: Upcoming MedMorph Meetings
Next Full TEP Meeting
  Tuesday January 19, 2021, 3-4 pm ET / 2-3pm CT / 1-2 pm MT / 12-1 pm PT
Reference Architecture Workgroup (Weekly)
  Resume January 6, 2021 - Wednesdays @ 1-2pm ET / 12-1pm CT / 11am-12pm MT / 10-11am PT
Consolidated Use Case Workgroups (Weekly)
  Next Meeting TBD January 2021 - Thursdays @ 12-1pm ET / 11-12 am CT / 10am-11 am MT / 9-10 am PT
Evaluation Workgroup
  Thursdays @ 10 -11 am ET/ 9-10 am CT/ 8-9 am MT/ 7-8 am PT

## Slide 25: Contacts
CDC Team
  Maria Michaels: ktx2@cdc.gov
  Wendy Blumenthal: wfb6@cdc.gov
  Arun Srinivasan: fos2@cdc.gov
  Syed Sameemuddin: puv5@cdc.gov
  Aaron Harris: ieo9@cdc.gov
  Brian Gugerty: vaz6@cdc.gov
  Cynthia Bush: pdz1@cdc.gov
TEP Co-Chairs
  John Loonsk: john.loonsk@jhu.edu
  Bill Lober: lober@uw.edu
Technical Leads
  Nagesh “Dragon” Bashyam: nagesh.bashyam@drajer.com
Support Team
  Becky Angeles: becky.angeles@carradora.com
  Jamie Parker: jamie.parker@carradora.com
  Kishore Bashyam: kishore.bashyam@drajer.com
  Mike Flanigan: mike.flanigan@carradora.com
Technical SME
  Brett Marquard: brett@waveoneassociates.com

## Slide 26: Appendix A: MedMorph General Information

## Slide 27
Agile Development: Iterative Design-Build-Test Cycles (test case: Hepatitis C)
Technical Expert Panel:
End Users, Data Recipients, Stakeholders – Including representatives of additional use cases
Fully Modeled Use Cases
Hepatitis C, Cancer, Healthcare Surveys
Technological Strategies
To develop scalable and extensible application
Fully Modeled Use Cases
Hepatitis C, Cancer, Healthcare Surveys
Technological Strategies
To develop scalable and extensible architecture
Implementation Guides
For general use and for each use case
Measure and Evaluate
PRODUCTS: Reference Architecture, Reference Implementation
(Open Source Software) & Balloted Implementation Guides, Roadmap for Scalability and Sustainability
Foundation of standards supported by health IT certification (CCDS/USCDI, APIs, FHIR)
Software
Clinical organization
EHR platform
Other testing partners (e.g., public health departments, registries, health IT developers, etc.)
National Test Collaborative
Including a variety of clinical organizations and their EHR platforms
Making EHR Data More Available for Research and Public Health
Evaluation Planning
CCDS: Core Clinical Data Set
USCDI: US Core Data for Interoperability
APIs: Application Programming Interfaces
FHIR: Fast Healthcare Interoperability Resources

## Slide 28: Helpful FHIR Links
FHIR Home Page & Summary:
  https://hl7.org/fhir/
  https://hl7.org/fhir/summary.html
FHIR Overview by user type:
  General: https://www.hl7.org/fhir/overview.html
  Developer: https://www.hl7.org/fhir/overview-dev.html
  Clinical: https://www.hl7.org/fhir/overview-clinical.html
  Architects: https://www.hl7.org/fhir/overview-arch.html
FHIR Implementation Guide Publishing: https://confluence.hl7.org/display/FHIR/IG+Publisher+Documentation
FHIR Implementation Guide Process Flow: https://confluence.hl7.org/display/FHIR/FHIR+Implementation+Guide+Process+Flow